## 📊 Overview
FMS Project Tracking — Overview
Contract: SMS-FMS-2026-001 ¦ Team: Ivan & Kelvin ¦ 3 Weeks Part-Time ¦ June 2026
Metric | Ivan | Kelvin | Combined
Total tasks | 48 | 42 | 90
Total est. hours | ~70.5hrs | ~68hrs | ~138.5hrs
Week 1 tasks | 13 | 12
Week 2 tasks | 19 | 18
Week 3 tasks | 16 | 12
API contracts (shared) | 11 checkpoints | 11 checkpoints | Must agree before coding
Deployment lead | Ivan | Supports | Week 3
Mobile portal | Backend only | Full UI | Head Technician portal
Status Legend
✅ Done | Task completed and deliverable working
🔄 In Progress | Currently being worked on
⏭ Deferred | Pushed to version update (log reason in Notes)
❌ Blocked | Blocked — log the blocker in Notes and tell your partner

## 🔵 Ivan
FMS Daily Tracking Checklist — Ivan ¦ 3-Week Part-Time Plan ¦ SMS-FMS-2026-001
Status options: ✅ Done ¦ 🔄 In Progress ¦ ⏭ Deferred ¦ ❌ Blocked Update the Status column daily. Add notes in the Notes column for blockers or context.
Day | Session | Deliverable / Task | Hrs | Status | Notes
WEEK 1 — Foundation, Orders & Auth
Weekend 1 · Day 1
Weekend 1 · Day 1 | Morning | Contabo VPS: Ubuntu 22.04 installed, SSH access confirmed, firewall rules set | 1.5
Weekend 1 · Day 1 | Morning | Nginx + PostgreSQL + Redis installed and running as services | 1.5
Weekend 1 · Day 1 | Afternoon | Django project created: apps scaffold (users, orders, production, stock, shop, notifications, reports, branches) | 2
Weekend 1 · Day 1 | Afternoon | Settings: .env config, CORS, JWT (simplejwt), Celery, Django Channels ASGI all wired up | 2
Weekend 1 · Day 2
Weekend 1 · Day 2 | Morning | Daphne ASGI server replaces Gunicorn — confirmed working with test endpoint | 1.5
Weekend 1 · Day 2 | Morning | JWT auth endpoints live: POST /api/auth/token/ + /api/auth/token/refresh/ — tested in Postman | 2
Weekend 1 · Day 2 | Afternoon | API CONTRACT AGREED with Kelvin: /api/auth/token/ request/response shape, JWT payload fields (role, branch_id) | 0.5
Weekend 1 · Day 2 | Afternoon | API CONTRACT AGREED with Kelvin: /api/orders/ POST fields, image upload multipart format, error shape | 0.5
Weekday Eve · Day 3
Weekday Eve · Day 3 | Evening | Order create API: POST /api/orders/ — validated, branch-scoped, returns 201 with order ref | 2.5
Weekday Eve · Day 4
Weekday Eve · Day 4 | Evening | Image upload endpoint: POST /api/orders/{id}/images/ — type/size validation (JPG/PNG, max 5MB) | 2.5
Weekday Eve · Day 5
Weekday Eve · Day 5 | Evening | Order list API: GET /api/orders/ — branch-scoped, status filter, pagination working | 2.5
Weekday Eve · Day 6
Weekday Eve · Day 6 | Evening | Order detail + dispatch API: PATCH /api/orders/{id}/ — status transitions, dispatch blocks if stages not DONE | 2.5
Weekday Eve · Day 7
Weekday Eve · Day 7 | Evening | Price confirm API: PATCH /api/orders/{id}/confirm-price/ — Director-only permission, order → OPS_QUEUE transition | 2.5
WEEK 2 — Workshop, Stock, SMS & Shop
Weekend 2 · Day 8
Weekend 2 · Day 8 | Morning | API CONTRACT AGREED with Kelvin: /api/production/stages/ shape, DONE endpoint response, material request body | 0.5
Weekend 2 · Day 8 | Morning | Stage assignment API: POST /api/production/stages/ — creates stages with sequence, technician FK, PENDING status | 2.5
Weekend 2 · Day 8 | Afternoon | Stage DONE endpoint: POST /api/production/stages/{id}/done/ — auto-activates next stage, updates order status | 2.5
Weekend 2 · Day 9
Weekend 2 · Day 9 | Morning | API CONTRACT AGREED with Kelvin: /api/stock/inventory/ ledger shape, issuance confirm body | 0.5
Weekend 2 · Day 9 | Morning | Material request API: POST /api/stock/requests/ — submit, PATCH approve/reject with reason, ISSUED state | 2.5
Weekend 2 · Day 9 | Afternoon | Inventory API: GET/POST/PATCH /api/stock/inventory/ — ledger CRUD, quantity tracking | 2
Weekend 2 · Day 9 | Afternoon | Issuance API: POST /api/stock/issuances/ — initial + additional issue, low-stock threshold alert trigger | 2
Weekday Eve · Day 10
Weekday Eve · Day 10 | Evening | API CONTRACT AGREED with Kelvin: /api/auth/pin/ body + JWT scope, technician work queue response fields | 0.5
Weekday Eve · Day 10 | Evening | Technician PIN auth: hashed PIN model, POST /api/auth/pin/ — returns limited-scope JWT for technician endpoints | 2
Weekday Eve · Day 11
Weekday Eve · Day 11 | Evening | Celery task: bulk SMS on order entry — all assigned technicians receive PENDING notification | 2.5
Weekday Eve · Day 12
Weekday Eve · Day 12 | Evening | Celery task: individual SMS on stage ACTIVE — single technician notification + SMSLog model + failure alert | 2.5
Weekend 3 · Day 13
Weekend 3 · Day 13 | Morning | API CONTRACT AGREED with Kelvin: /api/shop/items/ full shape, status enum values, SKU format | 0.5
Weekend 3 · Day 13 | Morning | Shop item API: GET/POST/PATCH /api/shop/items/ — CRUD, SKU validation, all 5 status values | 2.5
Weekend 3 · Day 13 | Afternoon | Set-breaking API: POST /api/shop/sets/{id}/break/ — Director-only, component re-pricing endpoint | 2
Weekend 3 · Day 13 | Afternoon | Reservation + sales API: create reservation, finalise to sale, expiry flagging, SOLD transition | 2.5
Weekend 3 · Day 14
Weekend 3 · Day 14 | Morning | Inter-branch transfer API: request, Director approval, inventory reassignment across branches | 2
Weekend 3 · Day 14 | Morning | API CONTRACT AGREED with Kelvin: /api/reports/ filter params + response aggregation shape, WS event payloads | 0.5
Weekend 3 · Day 14 | Afternoon | Reporting APIs: /api/reports/costs/, /payroll/, /sales/, slow-moving stock — all with branch + date filters | 3
Weekend 3 · Day 14 | Afternoon | WebSocket consumers: order update channel + stage update channel — event payloads defined and tested | 1.5
WEEK 3 — Integration, Testing & Deployment
Weekend 4 · Day 15
Weekend 4 · Day 15 | Morning | End-to-end order flow test with Kelvin: Front Desk create → Director approve → Ops assign (TC-F-001–015, TC-D-001–010) | 2.5
Weekend 4 · Day 15 | Afternoon | Workshop pipeline test with Kelvin: stage chain, SMS delivery, DONE → auto-activate (TC-O-001–013, TC-SMS-001–003) | 2.5
Weekend 4 · Day 16
Weekend 4 · Day 16 | Morning | Shop + stock flow test with Kelvin: sales, reservations, set-breaking, transfers, issuance (TC-SH-001–020, TC-S-001–011) | 2.5
Weekend 4 · Day 16 | Afternoon | Role access control audit: every role limited to correct endpoints — TC-AUTH-001–004, TC-R-009–011 all passing | 2
Weekday Eve · Day 17
Weekday Eve · Day 17 | Evening | Backend bug fixes from Weekend 4 testing — all identified issues resolved | 2.5
Weekday Eve · Day 18
Weekday Eve · Day 18 | Evening | PostgreSQL indexes added: branch_id, status, technician FK, SKU — query performance verified | 1.5
Weekday Eve · Day 18 | Evening | Reporting data accuracy check: margins, payroll totals, branch sales figures all verified correct | 1
Weekday Eve · Day 19
Weekday Eve · Day 19 | Evening | Remaining backend bug fixes — nothing unresolved going into deployment weekend | 2.5
Weekend 5 · Day 20
Weekend 5 · Day 20 | Morning | Nginx production config: reverse proxy, static/media file serving, HTTP → HTTPS redirect | 2
Weekend 5 · Day 20 | Morning | SSL certificate: Certbot Let's Encrypt installed, HTTPS confirmed live on domain | 1
Weekend 5 · Day 20 | Afternoon | Systemd services: Daphne + Celery worker running as auto-restart services — confirmed with systemctl status | 2
Weekend 5 · Day 20 | Afternoon | Environment hardening: SECRET_KEY, DB creds, SMS API key in .env, DEBUG=False confirmed | 1
Weekend 5 · Day 21
Weekend 5 · Day 21 | Morning | Automated DB backup: nightly pg_dump cron job, 14-day retention — test restore verified | 1.5
Weekend 5 · Day 21 | Morning | Smoke test on live server with Kelvin: all 5 roles log in, full order flow from front desk to dispatch | 2.5
Weekend 5 · Day 21 | Afternoon | Fix any deployment-environment issues: CORS, static files, WebSocket connections on live server | 2
Weekend 5 · Day 21 | Afternoon | System confirmed live — all modules operational, client handover checklist completed | 0.5
PROGRESS SUMMARY
| Metric | Formula
| Total tasks | 121
| ✅ Done | 0
| 🔄 In Progress | 0
| ⏭ Deferred | 0
| ❌ Blocked | 0
| % Complete | 0

## 🟢 Kelvin
FMS Daily Tracking Checklist — Kelvin ¦ 3-Week Part-Time Plan ¦ SMS-FMS-2026-001
Status options: ✅ Done ¦ 🔄 In Progress ¦ ⏭ Deferred ¦ ❌ Blocked Update the Status column daily. Add notes in the Notes column for blockers or context.
Day | Session | Deliverable / Task | Hrs | Status | Notes
WEEK 1 — Foundation, Orders & Auth
Weekend 1 · Day 1
Weekend 1 · Day 1 | Morning | PostgreSQL schema: Branch model + User model with role enum (5 roles) and branch FK — migration applied | 1.5
Weekend 1 · Day 1 | Morning | React project created with Vite: React Router v6, Axios, React Query installed and configured | 2
Weekend 1 · Day 1 | Afternoon | Role-based routing structure: 5 role portals scaffolded with protected routes and role guard HOC | 2.5
Weekend 1 · Day 2
Weekend 1 · Day 2 | Morning | Login screen UI: name/password form, role-based redirect on JWT decode, error states handled | 2.5
Weekend 1 · Day 2 | Morning | Axios interceptor: JWT attached to all requests, 401 triggers silent token refresh | 1.5
Weekend 1 · Day 2 | Afternoon | API CONTRACT AGREED with Ivan: /api/auth/token/ shape, /api/orders/ POST fields, error response format | 0.5
Weekend 1 · Day 2 | Afternoon | Order model + OrderImage model migrations — confirmed with Ivan before applying | 1.5
Weekday Eve · Day 3
Weekday Eve · Day 3 | Evening | Front Desk portal: order creation form — all fields, image upload component, validation messages | 2.5
Weekday Eve · Day 4
Weekday Eve · Day 4 | Evening | Front Desk portal: branch order dashboard — order list, status badges, delivery date display | 2.5
Weekday Eve · Day 5
Weekday Eve · Day 5 | Evening | Front Desk portal: status filter on dashboard, overdue order visual flag, dispatch button with guard | 2.5
Weekday Eve · Day 6
Weekday Eve · Day 6 | Evening | Director portal: price approval queue — order list with image thumbnails, full-size image viewer | 2.5
Weekday Eve · Day 7
Weekday Eve · Day 7 | Evening | Director portal: price confirm form — price input, confirm action, validation, released-to-ops confirmation | 2.5
WEEK 2 — Workshop, Stock, SMS & Shop
Weekend 2 · Day 8
Weekend 2 · Day 8 | Morning | API CONTRACT AGREED with Ivan: stage create body, stage list response, DONE endpoint, material request body | 0.5
Weekend 2 · Day 8 | Morning | ProductionStage + MaterialEstimate + MaterialRequest models and migrations — reviewed with Ivan | 2.5
Weekend 2 · Day 8 | Afternoon | Ops Manager portal: stage assignment panel — add stages, name, assign technician, set sequence, material estimates | 3.5
Weekend 2 · Day 9
Weekend 2 · Day 9 | Morning | API CONTRACT AGREED with Ivan: /api/stock/inventory/ shape, issuance confirm body | 0.5
Weekend 2 · Day 9 | Morning | Ops Manager portal: live pipeline dashboard connected to WebSocket — stage status updates in real time | 3
Weekend 2 · Day 9 | Afternoon | Ops Manager portal: material request approval queue — approve/reject with reason, confirmation states | 2
Weekend 2 · Day 9 | Afternoon | InventoryItem + Issuance models and migrations — reviewed with Ivan | 1.5
Weekday Eve · Day 10
Weekday Eve · Day 10 | Evening | API CONTRACT AGREED with Ivan: /api/auth/pin/ response, technician work queue fields for mobile UI | 0.5
Weekday Eve · Day 10 | Evening | Mobile portal: PIN login screen — name + PIN fields, touch-optimised, responsive layout on mobile viewport | 2
Weekday Eve · Day 11
Weekday Eve · Day 11 | Evening | Mobile portal: work queue — PENDING/ACTIVE stage cards, DONE button (disabled for PENDING), timestamps | 2.5
Weekday Eve · Day 12
Weekday Eve · Day 12 | Evening | Mobile portal: material request form + weekly earnings summary — submitted state, approved/rejected feedback | 2.5
Weekend 3 · Day 13
Weekend 3 · Day 13 | Morning | API CONTRACT AGREED with Ivan: /api/shop/items/ full shape, status enum, SKU format, /api/reports/ shape | 0.5
Weekend 3 · Day 13 | Morning | ShowroomItem + Reservation + Sale + BranchTransferRequest models and migrations — reviewed with Ivan | 2.5
Weekend 3 · Day 13 | Afternoon | Front Desk portal: showroom inventory view — branch-scoped item list, status badges, SKU search | 2
Weekend 3 · Day 13 | Afternoon | Front Desk portal: sales recording UI + reservation creation form with deposit field | 2.5
Weekend 3 · Day 14
Weekend 3 · Day 14 | Morning | Stock Keeper portal: inventory ledger, issuance queue, low-stock alerts, full order issuance history | 3.5
Weekend 3 · Day 14 | Afternoon | Director portal: set-breaking authorisation UI + component re-pricing form | 2
Weekend 3 · Day 14 | Afternoon | Director portal: inter-branch transfer approval UI + full reporting dashboard (cross-branch, filterable) | 3.5
WEEK 3 — Integration, Testing & Deployment
Weekend 4 · Day 15
Weekend 4 · Day 15 | Morning | End-to-end order flow test with Ivan: Front Desk create → Director approve → Ops assign (TC-F-001–015, TC-D-001–010) | 2.5
Weekend 4 · Day 15 | Afternoon | Workshop pipeline test with Ivan: stage chain, SMS notifications, DONE flow (TC-O-001–013, TC-T-001–012) | 2.5
Weekend 4 · Day 16
Weekend 4 · Day 16 | Morning | Mobile portal cross-device test: Android Chrome + iOS Safari — layout, touch, PIN login, DONE button | 2
Weekend 4 · Day 16 | Afternoon | Shop + stock test with Ivan: sales, reservations, set-breaking, transfers (TC-SH-001–020, TC-S-001–011) | 2.5
Weekday Eve · Day 17
Weekday Eve · Day 17 | Evening | Frontend bug fixes from Weekend 4 testing — all identified UI issues resolved | 2.5
Weekday Eve · Day 18
Weekday Eve · Day 18 | Evening | Reporting dashboard accuracy check: verify correct figures display for costs, payroll, sales by branch | 2
Weekday Eve · Day 19
Weekday Eve · Day 19 | Evening | Vite production build: output bundle verified, env vars set, static file paths confirmed for Nginx | 1.5
Weekday Eve · Day 19 | Evening | Remaining frontend bug fixes — nothing broken going into deployment weekend | 1.5
Weekend 5 · Day 20
Weekend 5 · Day 20 | Morning | Smoke test support: test all 5 portal UIs on live server — fix any broken routes, missing assets, WS issues | 2.5
Weekend 5 · Day 20 | Afternoon | Fix deployment-environment frontend issues: CORS errors, broken static paths, WebSocket connection on live URL | 2
Weekend 5 · Day 21
Weekend 5 · Day 21 | Morning | Final UI pass on live server: all portals responsive, all dashboards loading real data correctly | 2
Weekend 5 · Day 21 | Afternoon | System confirmed live — all 5 portals working on Contabo URL, mobile portal tested on real device | 0.5
PROGRESS SUMMARY
| Metric | Formula
| Total tasks | 109
| ✅ Done | 0
| 🔄 In Progress | 0
| ⏭ Deferred | 0
| ❌ Blocked | 0
| % Complete | 0